## Background and Coproduction
HNY Local Maternity and Neonatal System
Coproduced Equity and Equality Action Plan
01 April 2022 to 31 March 2022
The original scoping plan, aimed at identifying areas of local priority in HNY, was commenced in the Autumn of 2021, originally completed in December 2021, and submitted to the regional Maternity Transformation Team for oversight and further recommendations. A revised version was then derived from this initial plan; incorporating the recommendations made, additional information which had become available after the first submission, and some areas that other LMNSs had suggested should be included in an expanded plan. This was submitted in May 2022.
The scoping document and action plan have been developed in collaboration/informed following input from the following key stakeholders:
- Directors and Heads of Midwifery in the Trusts within our LMNS footprint: Hull University Teaching Hospitals NHS Trust; Northern Lincolnshire and Goole NHS Foundation Trust; York and Scarborough Teaching Hospitals NHS Trust
- LMNS Core Team
- Maternity Voices Partnerships
- LMNS/MVP Maternity and Neonatal Cultural Diversity Champion
- LMNS Delivery Board members including Senior Trust colleagues; Local Authority colleagues, ICS Perinatal Mental Health, Commissioners, MatNeo SIP, Y&H Clinical Network, NHSE regional and national maternity transformation colleagues and the Neonatal ODN.
- VSCE sector representatives
Action plan approval from LMNS Delivery Board prior to submission to NHSE regional maternity transformation team on 30/09/22.

## Action Plan
Limited/no progress to date
Some progress but more to be done
Completed/achieved
Priority | Deliverables | Actions/Interventions | By whom | By when | Target Group | Monitoring | Funding | Risks/issues | Status at September 2022
1/ Restore NHS Services inclusively by continuing to implement the COVID-19 4 actions | Increase the support for at risk pregnant women (lower threshold to review, admit and use MDT) | Ensure Trust guidance reflects the need for additional support for women and birthing people with a greater chance of poorer birth outcomes/complications. These include Ethnic Minority Groups, Deprived Communities, those who are homeless or in prison, those without access to services due to geography or digital exclusion, those with alcohol or substance misuse or who smoke or are overweight, those who need specialist physical or mental health support and those with disabilities or ongoing conditions. | Trusts with LMNS support | Ongoing; our core aim. | All as described. Specific focus on those requiring input from the Maternal Medicine Network. Links through to Perinatal Mental Health services for holistic support. | Regular review dates on guidance, risk profiles will be using the new Maternity IT System to identify gaps. | Equity funding (dependent on LMNS budgets). Links from the Maternity Clinical Network into training provision. | Ongoing identification of this group of users and direction of appropriate guidance in a timely way reliant on good two way communication. | Initial guidance reviewed during COVID, annual updates scheduled, working groups and digital midwives exploring technological support and digital inclusion.
| Reach out and reassure pregnant BAME women with tailored communications | Review LMNS Covid-19 web page. Ongoing COVID-19 targeted communications to all women and birthing people with an emphasis on Black, Asian and Minority Ethnic Groups (MEG), including on the use of folic acid, vitamin D and vaccinations. Ongoing COVID-19 vaccination myth busting/addressing misinformation and concerns/promoting vaccination as safe and advising on benefits. | LMNS Core Team LMNS 'Ask A Midwife' Trusts Comms & Maternity teams Childrens/Social Care partners | Ongoing throughout | Minority Ethnic Groups. Those living in areas of deprivation, crowded housing, coastal communities with poor transport links etc. | Web page reviewed & updated on a monthly basis. 'Ask A Midwife' service schedules posts on a regular basis. Targeted support for different ethnic groups via Cultural Diversity lead - workplan to be reviewed. Using ICS/VCSE/primary care partner communications. | No additional funding requirement. | Vaccine focus and provision of additional support in pregnancy not as high profile as previously. | COVID-19 web page reviewed Sept22. Monitoring use and page views regularly, 'Ask A Midwife' service still supporting queries. Local press involved in new publicity drive to coincide with Autumn Booster programme.
| Vitamins discussed with all women. Women with coloured or darker skin are recommended vitamin D. Folic acid recommended. | Review LMNS Covid-19 web page. Ongoing COVID-19 targeted communications to all women and birthing people with an emphasis on Black, Asian and Minority Ethnic Groups (MEG), including on the use of folic acid, vitamin D and vaccinations. Ongoing COVID-19 vaccination myth busting/addressing misinformation and concerns/promoting vaccination as safe and advising on benefits. Continue promoting messages in non-pregnant population to access those who may access pre-conception vaccinations and support, or those who have unplanned pregnancy. | LMNS Core Team Prevention Lead for diet/weight management LMNS AAM Trusts Comms & Maternity teams Childrens/Social Care partners | Ongoing throughout | Minority Ethnic Groups, particularly those with darker skin. Folic acid for many including specifically areas of deprivation. | Maternity IT System will allow audit of acceptance for specific support offers. | No additional funding requirement. | Vaccine focus and provision of additional support in pregnancy not as high profile as previously. | Birth education project has refreshed information on supplements and diet; rolling out currently.
| Record ethnicity, risk factors (such as co-morbidities, BMI and age), and postcode/ multiple deprivation index | Implementation of LMNS MITS BadgerNet will ensure maternity systems can record and show information needed on a consistent basis. Some information currently available via LMNS dashboard. | Trust IT Trust Procurement | Go live dates: YSTHFT - March 2023 HUTH - May 2023 NLaG - July 2023 | All Specific requirement to identify and support those who are homeless or incarcerated to ensure links with appropriate services. | Maternity IT System Steering Group/Digital Midwives to ensure compliance at system go-live. | Digital Maternity Fund/United Tech Fund. | Other IT implementations in some areas (NLaG EPR) may delay. | This information currently reflected on the LMNS dashboard, however no mandatory requirement for metric fields to be completed or uploaded to digital systems in present systems. This will support this ambition from rollout.
2/ Mitigate against digital exclusion | Ensure PCPs are available in a range of languages and formats, including hard copy for those experiencing digital exclusion Support the ICS Digital Inclusion workstream | LMNS has tailored communications relating to the PCP in different formats on website: - Hearing and sight loss - narrated video - Learning disabilities - pictorial version - Most common spoken languages - Romanian language and Polish subtitled videos - Paper version of PCP available when required. Reachdeck/Browsealoud on HUTH website - Procurement of Reachdeck for LMS website Patient facing app will incorporate PCPs - Badgernet in place at all Trusts by Dec 23. Digital Inclusion workstream includes identification of geographical areas of limited connectivity, identification of families without local connectivity due to access or cost, and those who do not have appropriate skills to access information. | LMNS Core Team LMNS Choice and Personalisation Group Digital Midwives All | Completed June 2022 End March 2023 December 2023 Ongoing attendance at meetings and forming strategy | All Visual birth plan in place; other plans to be made visual and accessible for those with learning disabilities. Management of requirements of Ukrainian refugees. Consider Trauma Involved care. Hard copy availabilty in clinics but also partners such as Children's Centres to hold. Support for resource to enable better access to mitigate these issues. | Review of usage via website downloads and printed version requirements. Maternity IT System will link through to alternative versions when implemented. Digital Inclusion workstream oversight | Communications allocated £10k each financial year to work with basic requirements. Other funding bid for in personalised care and other ICS/NHSE opportunities. Badged currently against equity funding for all areas. ICS Digital Strategy, Trust and LMNS strategies all include potential areas for bids (including UTF). | Reliant on capacity to co-produce video and other support communications with members of these communities. Resource availability and prioritisation across the area. | Ongoing procurement work for Reachdeck for the LMNS to support existing translation and interpretation support within Trusts. iPads being made available in Maternity and Neonatal Units currently to support information availability and allow interaction with websites and social media.
3/ Ensure data sets are complete and timely | Ensure maternity systems continuously improve the data quality of the ethnic coding and mother's postcode | MSDS data contains valid postcode on 95% of women booked in the month. | Trusts | Ongoing | Deprived Communities Homeless/incarcerated | Currently via Trust dashboards, new MITS will support. | No additional funding requirement. | Timing of MITS implementation. | As above; can be reported, but no mandated digital fields currently.
|  | Ensure MSDS includes valid ethnic category for at least 80% of women booked. Not stated, missing, and not known are not valid records. | Trusts | Ongoing | Minority Ethnic Groups | Currently via Trust dashboards, new MITS will support. | No additional funding requirement. | Timing of MITS implementation. | As above; can be reported, but no mandated digital fields currently.
|  | Ensure that each maternity system can display the multiple deprivation index number in the patient record, and report on it. | Trusts | Ongoing | Deprived Communities (including focus on coastal communities) | Currently via Trust dashboards, new MITS will support. | No additional funding requirement. | Timing of MITS implementation. | As above; can be reported, but no mandated digital fields currently.
4a/ Accelerate preventative programmes - understand your population and co-produce interventions | Understand the local population, it's health outcomes and community assets | LMNS Equity and Equality Analysis completed - last reviewed May 2022. Prevention/service user focused posts recruited to implement targeted work and assist in understanding of the needs of local populations: - LMNS Prevention Leads in post - Weight Management/Alcohol Misuse & Smoking in Pregnancy - MVP Group Lead in post and local MVP Group Chairs - September 2022 - Maternity and Neonatal Care Diversity Champion in post - February 2022 - Planned recruitment of LMNS/Maternal and Perinatal Mental Health Equity and Equality Lead. - Currently scoping work around Dads and Partners including the 'invisible dad' project - Work with partners to identify those with complex social factors and address the impact | LMNS Core Team MVPs LMNS E&E Lead LMNS/MVP Cultural Diversity Champion Commencing work with organisations such as the YMCA and NSPCC around dads/partners | May 2022 MVP review 22/23, phased growth from 23/24 December 2022 | All Those with specific and severe addiction or dietary needs (including diabetics, those with eating disorders, chrohns disease, coeliacs etc.) Those with casual substance misuse issues Those with ongoing issues after child(ren) requiring neonatal care Work with infant feeding coordinators to identify other key groups around diet and health outcomes. | LMNS Delivery Board MVP Group meetings LMNS Enablers Prevention Working Group | Funding allocated to Prevention Leads Funding allocated to MVP leads and expenses Funding allocated to Diversity Champion and E&E roles Review of MVP support planned for Q3 22/23 | Expected that additional funding and resource needs to be available across ICS to support MVP role expansion. Risk to growth with funding. | Updated scoping plan from May22 feeding these required actions. Prevention leads progressing specific LTP and related projects. MVP lead and chairs coming into post; LMNS and York Leads attended September national training session. E&E lead has confirmation from PNMH team of joint financial and resource support; with HR for advertisement.
| Understand staff experience, using Workforce Race Equality Scheme data | Baselines WRES assessment of the experience of maternity and neonatal staff by ethnicity included in Equity and Equality Analysis. Further work required as information not available in correct format. Work on next stages of diversity and inclusion in the workforce (including diabilities) from 2024/25 onwards. Promotion of all types of workforce diversity. | Trusts HR Trust Recruitment and Retention Leads Disability charities and workforce provision. | 2023/2024 2024/2026 | Minority Ethnic Groups (initially) To expand workforce support to those with other disabilities, health issues or similar to support a diverse workforce. | Trust HR T&F Group to be established to complete further work on WRES data. Continued work with Enablers Workforce Group. Links with ICS LEAP/HEE supported opportunities, education and training. | No additional funding requirement. | Trust systems working to provide relevant information regularly, however many competing priorities for IT development. | Ongoing liaison with Trust HR teams to support maternity teams with emphasis on culture. Staff perspective and comments gathered for inclusion and use in communications. Part of patient facing communications plan for these actions.
| Use this understanding to plan coproduction activity to design interventions to improve equity for women and babies and race equality for staff | AAM podcasts on maternity hot topics to break down boundaries on perceptions of maternity and neonatal practitioners and services. Communication campaign (posters/factsheets/outreach work) re access to maternity services for communities (particularly Eastern European and Romanian) that have low awareness of maternity pathways and referral systems, do not know that maternity is free at point of access. Scope the feasibility of setting up community hubs targeted at specific Minority Ethnic Groups. New Maternity IT System supporting work on reviewing booking processes for rapid referral and transit through pathways. | Trusts HR MVPs LMNS Core Team | 2023/2024 2024/2025 | All Specific focus for communities from Eastern Europe, Chinese and minority ethnic populations that are high in our communities as identified at scoping. | LMNS Choice and Personalised Care Working Group MVP Group ICS partners including social care and council support. Digital Midwives next steps after implementation. | Existing funding for communications and support used. Work with ICB/ICS to access additional health inequalities funding for support for communities. | Access to communities reliant on work with those populations, additional progress over next five years developing community relationships. | Podcasts being recorded with support from comms teams currently. Ongoing support for communications via social media and Ask A Midwife project. Some initial conversations with VSCE colleagues across the ICS, Healthwatch involvement with LMNS Cultural Diversity Lead ongoing. Digital Midwives working to implement new IT System, next steps about providing consistent, effective pathways.
4b/ Accelerate preventative programmes - action on maternal mortality, morbidity and experience | Ensure equity in access, experience and health outcomes for women from Black, Asian and Mixed ethnic groups and those women living in the most deprived areas. The LMNS may consider other protected characteristics and inclusion groups | Implement and maintain maternal medicine centres to help achieve equity, as part of the Maternal Medicine Network (MMN). | Maternal Medicine Network for Y&H Support from LMNS Core Team | Ongoing Q3 22/23 initial commencement Q4 22/23 staff and service user comms 23/24 ongoing pathway and staff development | Those requiring additional physical or mental health support pre-conception/pregnancy/birth/post-natal | MMN workstream steering group/pathways group/Oversight & Assurance | MMN Funding (recurrent from central NHSE funding) | Risk register held by MMN; highest issue is staffing capacity as new trainees required. | Key personnel recruited - programme will commence initially on epilepsy pathways from October 2022. Ongoing training of two Consultant Obstetricians progressing. Staff and user comms booked and then 23/24 plans to be further developed.
|  | Implement maternal mental health services with a focus on ethnicity and deprivation. | Maternal and Perinatal Mental Health Team | Ongoing (from 2022/23) | Minority Ethnic Groups Deprived Communities Those suffering loss (stillbirth, recurrent miscarriage, IVF failure, removal of newborns etc.) | PNMH/MMH Steering Groups and reporting to LMNS Delivery Board | PNMH/MMH funding recurrent from NHSE. | Joint working well embedded; staff capacity is the potential issue. Risk register sits with PNMH. | New Maternal Mental Health Service operational from Q1 22/23. Working together to further identify service users at risk and link into other supporting services.
|  | Work towards ensuring the MVPs in LMNS reflect the ethnic diversity of the local population, in line with NICE QS167 (promoting health and preventing premature mortality in Black, Asian and other minority ethnic groups). MVPs not representative at present but LMNS/MVP Cultural Diversity Champion recruited in February 2022. Next phase to address other protected characteristics; particularly those around gender and sexuality. | LMNS Core Team MVPs LMNS E&E Lead LMNS/MVP Cultural Diversity Champion | Ongoing; priority for 22/23 and 23/24 in embedding BAME support. | Minority Ethnic Groups Those with protected characteristics | MVP Groups Neonatal ODN Service User Representatives | Equity and MVP funding available. Anticipated additional funding linked to health inequalities programme to become available over next 5 years. | Using cultural diversity workplan to drive change. | LMNS/MVP Cultural Diversity Champion establishing links with MEG. All MVP Chairs aware of the requirement to broaden their membership. New chairs coming in from September 2022 to progress requirements.
|  | Increase working with VCSE sector to strengthen pathways to maternity services by ensuring representation on LMNS Working Groups/Board as appropriate/work of Maternity and Neonatal Cultural Diversity Champion and LMNS Equity and Equality Lead when in post. | VCSE sector (including housing support organisations) LMNS Core Team | Ongoing E&E post recruitment planned for Dec 2022 | All | Via Cultural Diversity workplan into LMNS Delivery Board | No additional funding requirement. | Large number of small groups risks split focus | Established links with the VCSE. Some attendance at working groups, to continue to grow.
|  | Outreach work planned to target underrepresented groups across HNY to improve current inequity in health outcomes. | LMNS Core Team Trusts Maternity teams ICS Population Health Board | 2023/24 | Focus on underrepresented groups within our communities | Via Cultural Diversity workplan into LMNS Delivery Board | Funding allocated to Prevention Leads Funding allocated to Diversity Champion and E&E roles Review of MVP support planned for Q3 22/23 | Large number of small groups risks split focus | Some specific work done on care planning for those going through surrogacy, support for those expecting a baby with Down Syndrome, and those with reading difficulties.
|  | Consider the significant impact on health and wellbeing linked to the cost of living crisis (2022/23) on all our underrepresented groups, including those living rurally who will potentially be more affected by high fuel costs. Increase working with local authorities/support agencies, ensure effective signposting and follow up. | Trusts Maternity teams VSCE Sector MVPs LMNS AAM | 2022/23 2023/24 | Those in deprived communities Those homeless or with housing issues Newly qualified/low income staff groups | Via Delivery Board and ICS Population Health Board Feeds into Council run 0-19 and Start for Life working groups. Links to Trust support programmes for staff | No additional funding requirement. Potential to work with Trust and HEE for staff development and support. | Scale of issues currently significant, already seeing postponement of training due to loss of enhanced shift payments. | Number of staff development schemes in place; LMNS already linked into Children & Young People's Alliance, and groups across each of the places.
|  | Targeted work to allocate additional resources and support to pregnant women and birthing people within our homeless communities. Physical and mental health support to be offered. | Trusts Maternity teams VSCE Sector | Expecting surge in demand from March 2023 when current mitigating actions cease. Recovery from recession anticipated up to 2025. | Pregnant women and birthing people who are homeless. | Via Delivery Board | No additional funding requirement. | Post-COVID support for homeless reduced. | Close working with the ICS Inclusion Primary Care Lead, to progress specific communications further.
|  | Initiate/obtain funding for a holistic weight management programme which targets pregnancy and the postpartum period and aims to reduce the rates of maternal obesity and improve outcomes for women and their babies. Links into the provision of Continuous Glucose Monitors for women with Type 1 diabetes; this project is on target at present. | LMNS Prevention Leads | 2023/24 through to 2025/26 | Women and birthing people who are overweight or obese at start of pregnancy, or who gain excessive weight during pregnancy. | Via ICS Population Health Board | Funding bid submitted September 2022 with 3 year plan for investment. | Bid may not be supported or funding available for future years. | Bid reviewed at ICS Population Health Board 28/09/22. Drawn up jointly with LMNS Prevention Lead and place public health commissioners.
4c/ Accelerate preventative programmes - action on perinatal mortality and morbidity | Address the leading causes of perinatal mortality and morbidity for Black, Asian, and Mixed ethnic groups and women living in the most deprived areas. The LMNS may consider other protected characteristics and inclusion groups | Implement targeted and enhanced continuity of carer across the system, ensuring women from Black, Asian, and Mixed ethnic groups and women living in deprived areas are prioritised with 75% of women in these groups receiving CoC by 2024. Ensure more midwifery time is allocated to support women from deprived areas. | LMNS Core Team Better Birth Leads Trusts Maternity Teams | 2023/24 | Specific focus in MCoC targets on BAME and Deprived Communities. | LMNS Choice and Personalised Care Working Group LMNS Delivery Board | Funding allocated for local leadership and support for equity plans. | Implementation affected by the current pause (insufficient staffing impacting safety in core service) in COC at HUTH, YSTHFT and Scunthorpe General Hospital | Initial pause implemented in HUTH/YSTHFT Trusts from May 2022. Currently some teams supported and ongoing in these groups in Northern Lincolnshire. Pause in MCoC targets announced September 2022; yet to understand how this impacts the 5 year plan.
|  | Implement a smoke-free pregnancy pathway - this offer is universal but there is ongoing work to ensure equity of access in all areas. | LMNS Prevention Leads Trusts Maternity Teams | 2022 onwards | Those smoking in pregnancy, their partners and families. Those who have previously quit in pregnancy and then restarted. | LTP Programme Boards LMNS Delivery Board | Long Term Plan funding | High prevalence of smoking in the area provides ongoing challenge. | Significant progress made as reported to LMNS Delivery Board. Initial offer in HUTH and NLaG - YSTHFT and HDFT to follow. Rates starting to fall in 22/23.
|  | Implement an LMNS Breastfeeding and Infant Feeding Strategy and continuously improve breastfeeding rates for women in the most deprived areas. This will also provide focus for younger parents who are less likely to breastfeed throughout. | LMNS Prevention Leads LMNS Core Team HNY ICB/ICS | Ongoing LMNS/ICS breastfeeding strategy to be completed during 2022/23. Promotion and links to Start for Life projects to continue. | Deprived Communities Additional staff offer | T&F group to be established to develop strategy. LMNS Choice and Personalised Care Working Group LMNS Enablers Prevention Working Group | Working with Council teams to obtain and allocate Start for Life funding streams. | Previous work done on infant feeding proved some very entrenched behaviours. New and innovative projects required. | LMNS working alongside existing projects and programmes. Previous success in investing funding for breastfeeding support in neonatal areas, deprived communities and early education environments.
|  | Permission will be sought to use resources developed by WY&H LMNS around the establishment of culturally sensitive genetic services for consanguineous couples. Our Equity and Equality Analysis tells us that demand in HNY will not be significant. | Trusts Maternity Teams LMNS Core Team | 2023/24 | Minority Ethnic Groups where consanguineous relationships are more prevalent. | LMNS Choice and Personalised Care Working Group Cultural Diversity Lead involvement. | No additional funding required. | Low volumes may mean these are not easily identified by midwife teams; education and training also required. | No current focus.
4d/ Accelerate preventative programmes - support for maternity and neonatal staff | Equip maternity and neonatal staff to provide culturally competent care Ensure maternity and neonatal staff experience race equality in the workplace | Roll out MDT and appropriate training for cultural competence in maternity and neonatal services. | Trusts Maternity Teams Trusts HR Teams | Spring 2023 onwards (once both roles in post) | All staff groups | Equity and Equality and Cultural Diversity Leads to progress. | No additional funding required. | Large programme of training required, on top of statutory training for midwives and other health professionals. | Identification of appropriate training underway.
|  | Sheffield Maternity Cooperative commissioned course on cultural competence in maternity for students at University of York. | University of York | First course held September 2022; to review outcomes and plan more. | Midwifery student groups | Universities in the LMNS to promote further (York and Hull). | No additional funding required; sits as part of University training. | Value and capacity of courses to be assessed. | Initial review to commence shortly, ongoing decisions then to be made.
|  | Consider commissioning competency/cultural safety training/workshops for maternity and neonatal staff. | Trusts Maternity & Neonatal Teams LMNS Core Team | 2023/24 onwards | All staff groups | Training plan currently being worked up with HEE. | No additional funding required. | LMNS working with HEE to prioritise courses; will not be sufficient funding for all requests. | Discussions for 23/24 work programme currently ongoing.
|  | When investigating SIs, consider the impact of culture, ethnicity, and language - % of maternity and neonatal SIs relating to patient care with a valid ethnic code - % of PMRT cases with a valid ethnic code. | LMNS Core Team Trusts Maternity teams | Current and ongoing | Maternity and Neonatal Teams | LMNS SI Overview Group LMNS Perinatal Quality, Safety and Assurance Group | No additional funding required. | Will require to audit requirements are being adhered to; current audit resource low. | PMRT and SI's currently being reported to Boards and LMNS. Audit of compliance yet to commence.
4e/ Accelerate preventative programmes – enablers | Create the conditions to help achieve equity by: - considering the factors that will support high quality clinical care - working with system partners and the VCSE sector to address the social determinants of health | Scope feasibility of community hubs in areas with the greatest maternal and perinatal health needs. Identify groups who could best benefit from local hubs including Gypsy and Traveller communities. | LMNS Core Team HNY ICS/ICB Better Birth Leads PNMH teams | 2023/24 | Deprived Communities | Partners in VCSE and Inclusion Oversight at LMNS Delivery Board | No additional funding required for initial scoping stage. | May need additional support as progresses. | No current focus.
|  | Work with system partners and the VCSE sector to address the social determinants of health. | VCSE Trusts Maternity LMNS Core Team HNY ICS ICB | 2022/23 onwards | All across LMNS projects and programmes | Delivery Board, ICS Population Health Board | No additional funding required. | May need additional support as progresses. | Maternity IT System will support further identification of where social determinants of health can be linked to other LMNS projects.
5/ Strengthen leadership and accountability | Plan to set out how the NHS will work in partnership to improve equity for women and babies and race equality for staff. The plan should be agreed by the LMNS board and the ICS partnership board and published. | Ensuring the action plan - Align to ICS plans to tackle health inequalities - Includes clear description of the LMNS population and health outcomes - Strong evidence of co-production - Relevant interventions in priorities 1-4 addressed - Ensure plan aligns to the population of our LMS (CORE 20+5). Interventions that are most likely to reduce health inequalities in our population - include actions/ milestones/ metrics, with responsible owners, timescales, and monitoring arrangements - a clear mechanism for ensuring continuous quality improvement - Include roles/ responsibilities, including ICS Board, LMNS SRO, Board level safety champions, MVP's - Detail any interdependencies with other ICS workstreams - Funding information - High level communication plan for stakeholders. | LMNS Core Team All HNY LMNS (including all staff, service users, health and social care professionals supporting this work. | Ongoing, and using this plan for the next 5 years. Regular review at the nominated groups to take place and the document to be updated as work progresses, new requirements are identified, and additional resource enters the system. | All | LMNS Delivery Board MVP Group meetings ICS Quality and Safety Group ICS Equity and Equality Group (with ICS EDI leads in attendance) | All project funding to support cultural diversity aspects and equality and equity requirements at all times. | Capacity and resource to be provided for all projects and importance of the consideration of all actions resulting from this plan to be highlighted. | Plan reviewed at LMNS Delivery Board September 2022. Current work to continue to provide insight and perspective onall areas of inclusion, diversity, equity and equality throughout all workstreams.
HNY Local Maternity and Neonatal System
Coproduced Equity and Equality Action Plan
01 April 2022 to 31 March 2027
Setting out actions to reduce mortality and morbidity of mothers, birthing people and babies, in the groups (Black, Asian and Minority Ethnic Groups and those living in our most deprived areas) experiencing significant and enduring health inequalities; and to achieve race equality for staff.
Action Owners
LMNS Core Team
LMNS AAM
LMNS Prevention Leads
HNY ICB/ICS
Maternal and Perinatal Mental Health Team
Trusts Maternity
Trusts HR
Trusts IT
Trusts Comms
Trusts Procurement
Trusts Recruitment and Retention Leads
Maternal Medicine Centres (MMC)
Trust Retention and Recruitment Midwives
Trust Better Birth Leads
LMNS E&E Lead
LMNS/MVP Cultural Diversity Champion
MVPs
VSCE sector
University of Hull
University of York
Targeted/underrepresented group
Black, Asian and Minority Ethnic Groups (MEG)
Faith groups (FG)
People in our more deprived communities (DC)
Physical disability (PD)
Mental disability (MD)
Learning disabilities (LD)
LGBQT+
Gypsies & travellers (G&T)
Prison population (PP)
Refugees and asylum seekers (R&AS)
Homeless (H)
HNY LMNS Trusts
HUTH - Hull University Teaching Hospitals NHS Trust
NLaG - Northern Lincolnshire and Goole NHS Foundation Trust
YSTHFT - York and Scarborough Teaching Hospitals NHS Foundation Trust